## Log Book data
Available tasks | Activity Result | Meaning
Background research | Completed | done for now
| In Progress | current activity
ANALYSIS AND DESIGN | Refined | was completed / finalised, has been changed
Research analysis (parsing research) | Finalised | submitted for review
Pseudocode creation | Cancelled | no longer part of the project
Flowchart creation
UML creation
DEVELOP PROTOTYPE
Project development
Project demonstration
Software optimisation
TESTING, EVALUATION/VALIDATION
Input and output testing
Graphics testing
Performance testing
ASSESSMENTS
Poster
Project documentation
Final demonstration/presentation
Other

## Log Book
Date | Week Num | Task (Phase Name) | Task Information (Sub phase name) | Comments | Result of activity | Status of activity | Future Notes
2017-09-29 | 0 | Other | Project Initiation Document | Project Initiation document has been submitted for review |  | Finalised
2017-10-04 | 1 | Background research | Looking at existing research papers on zombie mathematics | found a good starting point for the formulas the simulation can be based on |  | In Progress | source: http://mysite.science.uottawa.ca/rsmith43/Zombies.pdf
2017-10-05 | 1 | Background research | "" |  |  | Completed
2017-10-06 | 1 | Background research | Different parameters which could be used in the simulation |  |  | In Progress
2017-10-07 | 1 | Background research | "" |  | refining the formula and brainstorming possible parameters for the simulation | Completed | Separate classes of removed zombies from destroyed zombies, because some corpses cannot be reanimated if destroyed. As well as figure out how to make the zombies decay.
2017-10-09 | 2 | Background research | Different type of zombies in media | 2 types of zombies, slow and fast; speed and durability of zombies as parameters |  | In Progress
2017-10-10 | 2 | Background research | "" |  | 2 more parameters that can be implemented | Completed
2017-10-11 | 2 | Background research | Other factors in the simulation - the transmission parameter |  |  | In Progress
2017-10-12 | 2 | Background research | "" |  |  | Completed
2017-10-12 | 2 | Background research | Other factors in the simulation - natural death rate parameter |  |  | In Progress
2017-10-13 | 2 | Background research | "" | Useful website, data.worldbank.com which has data about countries |  | Completed | CSV file format for the data
2017-10-13 | 2 | Other | Meeting with Atta Badii, project supervisor | Talking about ideas for the design stage | Starting to think of UML designs, colour schemes, especially for colour blind users | Completed
2017-10-14 | 2 | Background research | Zombie conversion ratio |  |  | In Progress
2017-10-16 | 3 | Background research | "" |  |  | Completed
2017-10-18 | 3 | Background research | Researching other development environments and programming languages | Choosing to use C++ in a Visual Studio 2017 IDE | Chosen a programming language and an IDE to create the project in | Completed | Research SDL and SFML
2017-10-19 | 3 | Background research | Research of SFML, SDL and DirectX | I already have experience with SDL, SFML seems easier to integrate with other libraries. DirectX looks like hell |  | Completed | Possibly going to end up with SDL, since no other graphics libraries may be used
2017-10-21 | 3 | Background research | Researching how to statically link the SDL libraries | Static linking ensures that the release build i.e. end application does not have too many libraries, because they'd be embedded in the executable | Improves quality of life for end user | Completed | apply to the application straight away and don’t change until te end of the project
2017-10-22 | 3 | Project development | Initiating the project by creating the Visual Studio project and linking all SDL files | Set up the project so that the release file only needs one dll | set up the project | Completed
2017-10-23 | 4 | Research analysis (parsing research) | Turning the notes into a document in the project documentation | A lot of notes to parse through |  | In Progress | continue parsing the extra parameters that can be included in the project
2017-10-25 | 4 | Research analysis (parsing research) | "" |  |  | Completed | Create use cases
2017-10-26 | 4 | Project development | Get the simulation to make a window |  |  | Completed | Make the simulator to have resizable windows
2017-10-27 | 4 | Project documentation | Setting up the project documentation and completing the project abstract |  |  | Completed
2017-10-29 | 4 | Project development | Restarting with JavaFX and Java language | Too many libraries to handle with SDL and C++, since GUI development requires multiple libraries with many dependencies |  | In Progress
2017-11-02 | 5 | Project development | Returning to C++ And VS |  |  | Completed
2017-11-03 | 5 | Project development | Cleaning up code to set up ImGui |  |  | Completed
2017-11-07 | 6 | Project development | Testing ImGui components to see what can be added to the project |  |  | In Progress
2017-11-14 | 7 | Project development | Fixing minor problems which cause UX annoyances |  |  | Completed
2017-11-21 | 8 | Project development | Adding project files to github repository to help keep track of the changes in the project |  |  | Completed
2017-11-24 | 8 | Project development | Setting up textures so that a map is displayed |  |  | Completed
2017-11-27 | 9 | Project development | Implementation of a zoom function | A break in ImGui exists where the menu bar does not work if the user begins with their mouse on the app window |  | In Progress
2017-11-29 | 9 | Project development | Implementation of frame limiting |  |  | In Progress
2017-12-01 | 10 | Other | Took a break for a few days | I need a rest
2017-12-04 | 11 | Project development | Attempt at fixing and therefore improving the zoom function |  |  | In Progress
2017-12-07 | 11 | Project development | Fixed the menu bar problem by removing a line: SDL_GetCurrentDisplayMode |  |  | Completed
2017-12-08 | 11 | Project development | Setting up the program to be able to parse data | country data which will be used to load the country data |  | Completed
2017-12-09 | 11 | Project development | Successfully able to load external data | removed zoom and pan because it broke, oops |  | In Progress
2017-12-11 | 12 | Project development | Created an image which is now the default map. Countries are now identifiable via mouse click |  |  | Completed
2017-12-12 | 12 | Project development | Rethinking how there should be a separate program to create scenarios; Sub project started for the scenario creator |  |  | In Progress
2017-12-13 | 12 | Project development | Panning and zooming reimplemented |  |  | In Progress
2017-12-14 | 12 | Project development | Continued work on scenario creator |  |  | In Progress
2017-12-20 | 13 | Other | Taking the week off, holiday and rest
2017-01-04 | 15 | Project development | Resuming with work | Worked on GUI inputs and outputs, user experience and interface work
2017-01-08 | 16 | Project development | Standardising the scenario file types |  |  | In Progress
2017-01-11 | 16 | Project development | Changing some data types to unsigned long long to be able to handle huge numbers because of population | Added some opengl libraries to the dependencies file so that I can work on the project on other computers, especially the labs which don't seem to have the windows sdk installed |  | Completed
2017-01-11 | 16 | Project documentation | Feedback form for supervisor |  |  | Completed
2017-01-13 | 16 | Project development | Implementation of data saving | Can now save scenarios | some user friendlyness fixes, i.e. auto linking of countries, input validations etc | In Progress
2017-01-14 | 16 | Project development | Mini test of previous additions |  |  | In Progress
2017-01-15 | 17 | Project development | Working on loading scenario data |  |  | In Progress
2018-01-16 | 17 | Project development | Progress on loadScenario function |  |  | In Progress
2018-01-18 | 17 | Project development | loadScenario function finished |  |  | Completed | Make this function be usable in the simulator as well
2018-02-13 | 21 | Project development | Finished Scenario Creator |  |  | Completed
2018-03-14 | 25 | Project documentation | starting to create project poster |  |  | In Progress
2018-03-24 | 26 | Project documentation | Poster completed and submitted |  |  | Completed
2018-03-26 | 26 | Project documentation | Creation of the project report | Most headings set out |  | In Progress
2018-03-26 | 27 | Other | Added MIT License to the project on GitHub |  |  | Completed
2018-03-27 | 27 | Input and output testing | Created a release build of the incomplete system for other people to check currently working systems |  |  | Completed
2018-03-29 | 27 | Project documentation |  |  |  | In Progress
2018-03-30 | 27 | Project development | minor adjustments to Scenario Creator and Main simulator |  |  | Completed
2018-03-31 | 27 | Project documentation | Progress on report | Halfway done with the report |  | In Progress
2018-04-05 | 28 | Project documentation | Progress on report |  |  | In Progress
2018-04-05 | 28 | Project documentation | Progress on simulator | Most inputs are set up |  | In Progress
2018-04-06 | 28 | Project development | Explaining extra tools used in documentation |  |  | Completed
2018-04-09 | 29 | Project documentation | Progress on report |  |  | In Progress
2018-04-09 | 29 | Project documentation | Progress on simulator |  |  | In Progress
2018-04-10 | 29 | Project development | Simulator allows users to switch between scenarios in the simulation |  |  | Completed
2018-04-10 | 29 | Project development | Users can choose which country the infection spreads from |  |  | Completed
2018-04-11 | 29 | Project development | More simulation settings |  |  | In Progress
2018-04-13 | 29 | Project development | Minor tweaks in Scenario creator to reflect changes in main simulator |  |  | Completed
2018-04-13 | 29 | Project development | Sliders not used to input instead of typing values in |  |  | Completed
2018-04-13 | 29 | Project documentation | Progress on report |  |  | In Progress
2018-04-17 | 30 | Project development | Simulator can now run epidemic simulations, but not zombies yet |  |  | In Progress
2018-04-17 | 30 | Other | Setting up presentation for the presentation and demonstration of the project | Noticed that this was late and also accidentally sent the wrong file to blackboard |  | Completed
2018-04-18 | 30 | Final demonstration/presentation | Demonstrate the project to a panel | It went well, presentation shown to panel is different to the blackboard version |  | Completed
2018-04-19 | 30 | Project documentation | Finishing the report |  |  | In Progress
2018-04-20 | 30 | Other | This is the last entry on the log book, if you want a complete version of every single commit, check out this project on blackboard | Note: Anything commited after 20/02/2018 is no longer part of the submitted document and is me working on improving the project outside of this |  | Completed